## Sheet
Bug ID | Title | Severity | Priority | Module | Expected Behavior | Actual Behavior | Impact | Status | Steps
CRIT-001 | Application not starting | Critical | P1 | System | Application starts and displays properly with validation on endpoints | 200 OK response but no content displayed | Application unusable | Closed (Fixed /public/index.php) | 1. Attempt to start Laravel application 2. Access application via browser 3. Observe 200 OK response with no display
CRIT-002 | SQLSTATE[42S02]: Base table or view not found: 1146 Table 'qa_assessment.sessions' doesn't exist | Critical | P1 | System | Session table automatically created during database migration, sessions handled properly | 500 Internal Server Error, authentication system fails, user sessions cannot be maintained | Blocks all authentication functionality, application unusable for session-based operations | Open (Workaround: Run `php artisan session:table` followed by `php artisan migrate`) | 1. Set up fresh Laravel application with MySQL database configuration 2. Configure database connection in `.env` file 3. Run application without executing session table migration 4. Attempt to access any route requiring session handling (e.g., login, registration) 5. Observe 500 Internal Server Error
HIGH-001 | Users can register with fake emails without verification | High | P2 | Authentication | Email verification required before login | Full access without verification | Fake accounts, spam potential |  | 1. Register with email "fake@nonexistent.com" 2. Login immediately without verification 3. Access all features
MED-001 | API returns different error formats across endpoints | Medium | P2 | System | Consistent error response format | Different structures and field names | Client-side error handling complexity |  | 1. Trigger validation error in /api/register 2. Trigger authentication error in /api/login 3. Compare error response structures
MED-002 | "test@example.com" and "Test@Example.COM" treated as different users | Medium | P3 | Authentication | Case-insensitive email handling | Case-sensitive email uniqueness, SQLSTATE[23000] constraint violation | User confusion, duplicate accounts, 500 Internal Server Error |  | 1. Register with "test@example.com" 2. Attempt register with "Test@Example.COM" 3. Observe duplicate allowed or constraint violation
CRIT-003 | Unlimited login attempts enable brute force attacks | Critical | P1 | Authentication | Rate limiting after 5 attempts | Unlimited attempts allowed | Account compromise vulnerability. |  | 1. Send 100+ consecutive login attempts with wrong passwords 2. Observe no blocking or delay 3. Continue attempts until account locked or credentials guessed
CRIT-004 | Missing store() method in UserController triggers 500 Internal Server Error | Critical | P1 | User Management | store() method exists in UserController, user created or validation errors returned gracefully | Method App\Http\Controllers\UserController::store does not exist, 500 Internal Server Error | User registration functionality completely broken, integrations fail, affects onboarding and API stability |  | 1. Send POST request to user creation endpoint (/users or /api/users) 2. Laravel attempts to call UserController::store() 3. Observe server response
CRIT-005 | User update endpoint accepts invalid data with no validation | Critical | P1 | User Management | Server validates all fields, returns 422 Unprocessable Entity for invalid input | Endpoint accepts any input including empty or malformed values, user record updated with bad data | Data integrity issues, invalid user accounts, security risks, dependent modules may fail |  | 1. Send PUT request to http://localhost:8000/api/users/1 2. Use invalid payload: {"name": "", "email": "not-an-email", "role": null} 3. Observe API response 4. Note that request succeeds
CRIT-006 | Regular users can grant themselves admin role | Critical | P1 | User Management | 403 Forbidden, role unchanged | 200 OK, role updated to admin | Unauthorized admin access |  | 1. Login as regular user 2. Send PUT to /api/users/self with {"role": "admin"} 3. Verify role change in response 4. Attempt admin operations
CRIT-007 | API allows identical product payload to be saved repeatedly without validation | Critical | P1 | Product Management | API validates unique fields (name, SKU) and rejects duplicates | Duplicate product entries are saved without warnings, no validation errors returned | Database pollution, inventory miscalculations, catalog inconsistencies |  | 1. Send the same product payload to POST /api/products more than 10 times 2. Observe that the API accepts the request every time 3. Check the database for duplicate records
CRIT-008 | Client can manipulate product prices during order creation | Critical | P1 | Order Management | Prices calculated server-side only | Client-provided prices accepted | Financial loss, revenue manipulation |  | 1. Login as user 2. Send POST to /api/orders with manipulated price values 3. Observe order creation with incorrect total
CRIT-009 | Users can access other users' orders by modifying URL parameters | Critical | P1 | Order Management | 403 Forbidden or 404 Not Found | 200 OK with other user's order data | Data privacy violation |  | 1. Login as user A (user_id: 5) 2. Send GET to /api/orders/10 (belongs to user B) 3. Observe order details returned
HIGH-002 | Product stock can be set to negative values | High | P1 | Product Management | Validation error for negative stock | Stock updated to negative value | Inventory management broken, ordering issues |  | 1. Login as admin 2. Update product stock to -5 3. Verify update successful
HIGH-003 | Deleting user leaves orphaned orders in database | High | P2 | User Management | Cascading delete or user_id set to null | Orders remain with deleted user_id | Data integrity issues, reporting errors |  | 1. Create user and associated orders 2. Delete user via API 3. Check orders table for user_id references
HIGH-004 | Product prices accept too many decimal places | High | P2 | Product Management | Price rounded to 2 decimal places | Excessive precision stored and calculated | Financial calculation errors |  | 1. Create product with price 19.999999 2. Calculate order total with multiple items 3. Observe incorrect financial calculations
HIGH-005 | User deletions and role changes not logged | High | P2 | System | All critical operations logged | No audit records created | No accountability, difficult investigations |  | 1. Delete multiple users 2. Change user roles 3. Check for audit trail
HIGH-006 | Deleting product breaks order history | High | P2 | Product Management | Order history preserved with product details | Order shows "product not found" or errors | Broken order history, reporting issues |  | 1. Create order with product 2. Delete the product 3. View order details
MED-003 | Order created_at uses UTC instead of local timezone | Medium | P3 | Order Management | Timestamps in configured timezone | Always UTC regardless of configuration | Reporting and display issues |  | 1. Create order in EST timezone 2. Check created_at timestamp in database 3. Compare with local time
MED-004 | Frequent product list requests cause database load | Medium | P3 | Product Management | Response caching for static data | Database query on every request | Performance issues under load |  | 1. Send 100 consecutive GET /api/products requests 2. Monitor database query logs 3. Observe same query executed each time
MED-005 | Cannot update multiple product prices at once | Medium | P3 | Product Management | Bulk update endpoint or batch operations | Individual updates required | Administrative inefficiency |  | 1. Attempt PATCH /api/products with multiple product updates 2. Observe error response
MED-006 | Orders can jump from "pending" to "delivered" skipping "shipped" | Medium | P3 | Order Management | Valid status transitions enforced | Any status can transition to any other | Business process violation |  | 1. Create order with "pending" status 2. Update directly to "delivered" status 3. Verify status change allowed
HIGH-008 | Simultaneous status updates can cause inconsistent state | High | P2 | Order Management | Consistent final status | Race condition, unpredictable final status | Order processing confusion |  | 1. Create order in "pending" status 2. Simulate two admin users updating status simultaneously 3. Check final order status
HIGH-002 | Concurrent orders can oversell products | High | P1 | Order Management | Second order fails due to insufficient stock | Both orders created, stock goes negative | Overselling, customer dissatisfaction |  | 1. Set product stock to 1 2. Simulate two users ordering simultaneously 3. Both orders created successfully
MED-007 | Cannot search orders by product name or customer email | Medium | P3 | Order Management | Search/filter capability on orders | No search parameters accepted | Administrative difficulty finding orders |  | 1. Attempt GET /api/orders?search=test@example.com 2. Observe no filtering applied
LOW-004 | Product list order changes between requests | Low | P4 | Product Management | Consistent default sorting (e.g., by name) | Database-dependent order, changes between calls | User experience inconsistency |  | 1. GET /api/products multiple times 2. Observe product order changes
LOW-005 | No endpoint to check API status and database connectivity | Low | P4 | System | Health check endpoint available | No dedicated health check endpoint | Monitoring difficulty |  | 1. Look for /api/health or /api/status endpoint 2. Attempt to access